## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2024-06-04 |  |  |  |  | June | [27 empty] | July
Scrolling Increment: | 1 | time axis 2024-06-05 to 2024-07-30
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-06-05 to 2024-07-30
TITLE 1
Task 1 | Goal | Name | 25% | 2024-06-04 | 3 | 2024-06-05: 2; 2024-06-06: 2
Task 2 | Milestone |  |  | 2024-06-09 | 1 | bar: 2024-06-09
Task 3 | Low Risk |  | 50% | 2024-06-01 | 10
Task 4 | Milestone |  |  | 2024-06-24 | 1 | bar: 2024-06-24
Task 5 | Med Risk |  | 10% | 2024-06-10 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-06-10 | 13
Task 2 | On Track |  | 50% | 2024-06-12 | 9
Task 3 | Low Risk |  | 33% | 2024-06-17 | 11
Task 4 | Milestone |  |  | 2024-06-19 | 1 | bar: 2024-06-19
Task 5 |  |  |  | 2024-06-20 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-06-19 | 4
Task 2 | Med Risk |  |  | 2024-06-22 | 14
Task 3 | On Track |  |  | 2024-07-07 | 6
Task 4 | Goal |  |  | 2024-07-11 | 3 | 2024-07-11: 2; 2024-07-12: 2; 2024-07-13: 2
Task 5 | Low Risk |  |  | 2024-06-10 | 19
TITLE 4
Task 1 |  |  |  | 2024-07-14 | 15
Task 2 |  |  |  | 2024-07-28 | 5
Task 3 | Milestone |  |  | 2024-09-08 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Dark
Chinese Palace - Website
JZTC |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
CEO Joenella Hiko
Project Start Date: | 2024-02-26 |  |  |  |  | April | [13 empty] | May | [27 empty] | June
Scrolling Increment: | 55 | time axis 2024-04-21 to 2024-06-15
]
Complete Iteration 1 progress report | Category | Assigned to | Progress | Start | Days | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
Complete stakeholder register | On track | Jo, Zoe, Tainui, Cairo | 100% | 2024-02-26 | 6
Split team into groups | On track | Class | 100% | 2024-02-28 | 3
Complete personas | Med Risk | Jo, Zoe, Tainui, Cairo | 100% | 2024-03-05 | 5
Complete persona reviews | Low Risk | Jo, Zoe, Tainui, Cairo | 100% | 2024-03-02 | 10
Complete group meeting report | Milestone | Jo, Zoe, Tainui, Cairo | 100% | 2024-03-04 | 1
Complete iteration 2 progress report | Category | Assigned to | Progress | Start | Days
Complete resources needs documentation | High Risk | Jo | 100% | 2024-05-02 | 13
Establish project times and devlierables using a gantt chart | On track | Tainui | 100% | 2024-05-07 | 9
Migrate task management from Google drive to Github repositories | Low Risk | Zoe | 100% | 2024-05-09 | 11
Complete iteration 2 group meeting report | Milestone | Jo, Zoe, Tainui, Cairo | 100% | 2024-05-09 | 1 | bar: T
Complete iteration 3 progress report | Category | Assigned to | Progress | Start | Days
Complete gantt chart | On track | Tainui | 50% | 2024-05-21 | 4
Finish final progress report | Med Risk | Jo | 100% | 2024-05-23 | 7
Clean the Github Repo. | High Risk | Tainui | 100% | 2024-05-22 | 6
Create a Kanban board, | Low Risk | Zoe | 0% | 2024-05-20 | 3
Conduct and document a group meeting | Milestone | Jo, Zoe, Tainui, Cairo | 100% | 2024-05-27 | 1 | bar: M
Formulas:
Start = [Start, row above]+5

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2024-06-04 |  |  |  |  | June | [27 empty] | July
Scrolling Increment: | 5 | time axis 2024-06-09 to 2024-08-03
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-06-09 to 2024-08-03
TITLE 1
Task 1 | Goal | Name | 25% | 2024-06-04 | 3
Task 2 | Milestone |  |  | 2024-06-09 | 1 | bar: 2024-06-09
Task 3 | Low Risk |  | 50% | 2024-06-01 | 10
Task 4 | Milestone |  |  | 2024-06-24 | 1 | bar: 2024-06-24
Task 5 | Med Risk |  | 10% | 2024-06-10 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-06-10 | 13
Task 2 | On Track |  | 50% | 2024-06-12 | 9
Task 3 | Low Risk |  | 33% | 2024-06-17 | 11
Task 4 | Milestone |  |  | 2024-06-19 | 1 | bar: 2024-06-19
Task 5 |  |  |  | 2024-06-20 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-06-19 | 4
Task 2 | Med Risk |  |  | 2024-06-22 | 14
Task 3 | On Track |  |  | 2024-07-07 | 6
Task 4 | Goal |  |  | 2024-07-11 | 3 | 2024-07-11: 2; 2024-07-12: 2; 2024-07-13: 2
Task 5 | Low Risk |  |  | 2024-06-10 | 19
TITLE 4
Task 1 |  |  |  | 2024-07-14 | 15
Task 2 |  |  |  | 2024-07-28 | 5
Task 3 | Milestone |  |  | 2024-09-08 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one